## Sheet1
Sr.No | Project | Task No | Task | Status | Description | Depend on Task | Task Start Date | Task Planned End Date | Task Actual End Date | Risk | Mitigation | Owner | Pending with | Remark 1 | Remark 2
1 | CRM | 1 | API Document Sharing and Working state | Completed |  |  | 2022-02-07 | 2022-02-17 |  |  |  | Setupathi | Setupathi/Murthy | Delayed in sharing the documents
| CRM |  | API Document sharing | Completed
| CRM |  | API working status | In Process | API need to hit twice to get the response
| CRM |  | User login credentials for API | In Process | There is login credentials provided for UAT/ For production we need to create it
| CRM | 2 | API Testing | Completed |  | 1 | 2022-02-07 | 2022-02-17 |  |  |  | Setupathi | Setupathi/Murthy | Delayed in sharing the documents
| CRM |  | Create Token API Testing | Open |  |  | 2022-02-14 | 2022-02-19 |  | API accessibillity issues can be occurred | Need technical support whenever required | Nikhil
| CRM |  | Get API Testing | Open | User login credentials required to be used in the API for API testing |  | 2022-02-14 | 2022-02-19 |  | API accessibillity issues can be occurred | Need technical support whenever required | Nikhil
| CRM |  | API Testing signoff | Open | API document with all data dictionary required |  | 2022-02-14 | 2022-02-19 |  |  |  | Nikhil
| CRM |  | Flow making of the process | Completed |  |  | 2022-02-14 | 2022-02-19 |  |  |  | Nikhil
| CRM | 3 | Requirenment gathering | Completed
| CRM |  | Master data required | Completed
| CRM |  | Get status API response data confirmation | Completed
| CRM |  | Requirenment for search by application ID | Completed | CRM Table Databases access given but not able to connect WSO2 with TCS MySQL DB to fetch the CRM ID against application ID request initiated with TCS team.
| CRM | 4 | Web form development | Completed |  |  | 2022-02-14 | 2022-02-16 | 2022-02-16 |  |  | Gopi
| CRM |  | Platform setup | Completed |  |  | 2022-02-14 | 2022-02-18 |  |  |  | Sourav
| CRM |  | CRM Creation webpage development | Completed |  |  | 2022-02-14 | 2022-02-18 |  |  |  | Gopi
| CRM |  | CRM get status webpage development | Open |  |  | 2022-02-14 | 2022-02-18 |  |  |  | Rashmi
| CRM |  | Testing functionality of the webpage of CRM ticket creation and Get status page | Open |  | 1
| CRM | 5 | Functional team Testing & Sign Off | In Process | New requirement recived, PAYTM Integration R&D Inprocess |  | 2022-02-21 | 2022-02-22 |  |  |  | Chandan
| CRM |  | Functional Team testing | Open |  |  | 2022-02-21 | 2022-02-23 |  |  |  | Chandan
| CRM |  | Functional Team Sign-off | Open
| CRM | 6 | Architecture Server and Design | Completed | [7 empty] | Ajinkya Sir/Sharad Sir
| CRM |  | Application and DB Setup | Completed
| CRM | 7 | Deployment on production server | Open | [7 empty] | Shalmali
| CRM |  | Production API Details | Open | Requested with murthy Ji | [6 empty] | Murthy
| CRM |  | User creation with non-expiry password on production | Open | [7 empty] | Murthy
| CRM |  | API whitelisting and Port opening | Open | [7 empty] | Nikhil
| CRM |  | Accessibility check and confirmation | Open | [7 empty] | Engineering Team
2 | Android Application for Internal users | 1 | Requirenment Gathering | Completed
| Android Application for Internal users |  | Scope of the project | Completed
| Android Application for Internal users |  | Technology discussion | Completed
| Android Application for Internal users | 2 | Platform setup | Completed
| Android Application for Internal users |  | Testing the platform with compabillity | Completed
| Android Application for Internal users |  | Android app development platoform decision and setup | Completed
| Android Application for Internal users |  | Backend platoform decision and setup | Completed
| Android Application for Internal users |  | API Call functionallity from Laravel to external testing | Completed
| Android Application for Internal users |  | API Call from Android to Laravel testing | Completed
| Android Application for Internal users | 3 | Android Application Development Process | Completed
| Android Application for Internal users |  | Android Application design and flow decision making | Completed
| Android Application for Internal users |  | List of API to be publish for android app | Completed
| Android Application for Internal users |  | Android app development process | In Process
| Android Application for Internal users | 4 | Webportal development process | Completed
| Android Application for Internal users |  | Web application design and development | In Process
| Android Application for Internal users |  | Process flow for portal | Completed
| Android Application for Internal users |  | Login form and Internal form creation process | Completed
| Android Application for Internal users |  | Table creation for project | Completed
| Android Application for Internal users |  | Fetching and showing table data on form | Completed
| Android Application for Internal users |  | Export excel feature for portal | Open
| Android Application for Internal users | 5 | Production deployement | In Process | Business Card required/Dynamic/HGS
| Android Application for Internal users |  |  | Open
| Android Application for Internal users |  |  | Open
| Android Application for Internal users |  |  | Open
3 | PD-Docket Scan Automation | 1 | Requirenment gathering | Completed
| PD-Docket Scan Automation |  | Create project flow for the process | Completed
| PD-Docket Scan Automation |  | Confirmation of project flow | Completed
| PD-Docket Scan Automation |  | Master data sharing | Completed
| PD-Docket Scan Automation | 2 | Development | Completed
| PD-Docket Scan Automation |  | Initiator form development and design | Completed
| PD-Docket Scan Automation |  | Initiator form validation | Completed
| PD-Docket Scan Automation |  | PD Search form development and Design | Completed
| PD-Docket Scan Automation |  | Search form validation | Completed
| PD-Docket Scan Automation |  | Table creation with backend development | Completed
| PD-Docket Scan Automation |  | Master data insertion | Completed
| PD-Docket Scan Automation |  | Process flow development | Completed
| PD-Docket Scan Automation |  | Group creation | Completed
| PD-Docket Scan Automation |  | User right assignement | In Process
| PD-Docket Scan Automation | 3 | Production deployement | In Process | API Integrated / Demo Pending
| PD-Docket Scan Automation |  | Business UAT Sign-Off | Open
| PD-Docket Scan Automation |  | SR Initiation | Open
| PD-Docket Scan Automation |  | New workflow creation in Production | Open
| PD-Docket Scan Automation |  | Table creation with backend development | Open
| PD-Docket Scan Automation |  | Master data insertion | Open
| PD-Docket Scan Automation |  | POA Sharing | Open
| PD-Docket Scan Automation |  | POA Approval | Open
| PD-Docket Scan Automation |  | CAB Approval | Open
| PD-Docket Scan Automation |  | Front end and backend movement from UAT to Production | Open
4 | LifeRay Product Application |  |  | Hold
5 | Office O365 Mail Integration |  |  | Hold
6 | Process Maker Form Conversion |  | Form List | In Process
|  |  | Ghar Vapsi Portal | In Process | Structure and Port Opening
|  |  | Transfer Request | Open
|  |  | Carrier Portal | In Process
|  |  | HR Document Portal | Hold
| Declaration form |  | Sign-off and production deployement | Completed
|  |  | Auto mail initiation | In Process
| GitHub Project Version maintainence |  |  | Hold
| AD User deactivation automation |  | Development completed | In Process | Sign-off pending
| Aadhar on the Go Sales mobillity Application Development |  | DMS Document Overview | Completed
| Customer Service Mobile Application |  | In Testing phase | In Process
| Neo Website Pending integrations (Lead, Payments,Mandate,Existing form movement) |  | Requirement and API Provided | In Process | https://pm.aadharhousing.com/careerportal.html https://pm.aadharhousing.com/hrDocument.html https://aadharhousing.com/gharVapsi.html https://aadharhousing.com/transferRequest.html
| Welcome Kit |  | Server and API provided | In Process
| DOB Real Time payment status check |  | Logic provided - dicussion pending | In Process
| Crif CIBIL API Testing |  |  | Hold
Laravel Lead form development

## Sheet2
Task Status
Open
Completed
In Process
Hold