## Sheet1
Sr.No | Project | Task No | Task | Subtaks | Description | Task Start Date | Task Planned End Date | Task Actual End Date | Risk | Mitigation | Owner | Status | Pending with | Dependent Task | Remark 1 | Remark 2
1 | CRM | 1 | API Document Sharing | API Document sharing |  | 2022-02-07 | 2022-02-17 |  |  |  | Setupathi | Pending | Setupathi/Murthy |  | Delayed in sharing the documents
1 | CRM | 1 | API Document Sharing | User login credentials for API |  | 2022-02-07 | 2022-02-17 |  |  |  | Setupathi | Pending | Setupathi/Murthy |  | Delayed in sharing the documents
1 | CRM | 2 | API Testing | Create Token API Testing |  | 2022-02-14 | 2022-02-19 |  | API accessibillity issues can be occurred | Need technical support whenever required | Nikhil | InQueue |  | 1
1 | CRM | 2 | API Testing | Get API Testing | User login credentials required to be used in the API for API testing | 2022-02-14 | 2022-02-19 |  | API accessibillity issues can be occurred | Need technical support whenever required | Nikhil | InQueue |  | 1
1 | CRM | 2 | API Testing | API Testing signoff | API document with all data dictionary required | 2022-02-14 | 2022-02-19 |  |  |  | Nikhil | InQueue |  | 1
1 | CRM | 2 | API Testing | Flow making of the process |  | 2022-02-14 | 2022-02-19 |  |  |  | Nikhil | InQueue |  | 1
1 | CRM | 3 | Web form development | Platform setup |  | 2022-02-14 | 2022-02-16 | 2022-02-16 |  |  | Gopi | Completed
1 | CRM | 3 | Web form development | Backend development |  | 2022-02-14 | 2022-02-18 |  |  |  | Sourav | InQueue
1 | CRM | 3 | Web form development | Front end development |  | 2022-02-14 | 2022-02-18 |  |  |  | Gopi | Completed
1 | CRM | 3 | Web form development | Testing functionality of the webpage |  | 2022-02-14 | 2022-02-18 |  |  |  | Rashmi | InQueue
1 | CRM | 4 | Functional team Testing & Sign Off | Functional Team testing |  | 2022-02-21 | 2022-02-22 |  |  |  | Chandan | InQueue
1 | CRM | 4 | Functional team Testing & Sign Off | Functional Team Sign-off |  | 2022-02-21 | 2022-02-23 |  |  |  | Chandan | InQueue
1 | CRM | 5 | Architecture Design | Application and DB | [6 empty] | Ajinkya Sir/Sharad Sir | InQueue
1 | CRM | 6 | Deployment on production server | API whitelisting and Port opening | [6 empty] | Shalmali | InQueue
1 | CRM | 6 | Deployment on production server | Accessibility check and confirmation | [6 empty] | Nikhil | InQueue
1 | CRM | 6 | Deployment on production server | Actual project deployment and Live | [6 empty] | Engineering Team | InQueue
2 | Android Application for Internal users
3 | PD-Docket Scan Automation | 1 | Requirenment gathering | Create project flow for the process
3 | PD-Docket Scan Automation | 1 | Requirenment gathering | Confirmation of project flow
| PD-Docket Scan Automation | 1 | Requirenment gathering | Master data sharing
3 | PD-Docket Scan Automation | 2 | Development | Initiator form development and design
3 | PD-Docket Scan Automation | 3 | Development | Initiator form validation
| PD-Docket Scan Automation |  | Development | Search form development and Design
|  |  | Development | Search form validation
|  |  | Development | Table creation with backend development
|  |  | Development | Master data insertion
4 |  |  | Development | Process flow development
5 |  |  | Development | Group creation
|  |  | Development | User right assignement
|  |  | Production deployement | Business UAT Sign-Off
|  |  | Production deployement | SR Initiation
|  |  | Production deployement | POA Sharing
|  |  | Production deployement | POA Approval
|  |  | Production deployement | Front end and backend movement from UAT to Production
LifeRay Product Application
Office O365 Mail Integration