## PR
| Total Project | Completed PR | Work IN Progress | Drop Project | On Hold Project
| 47 | 75 | 25 | 1 | 5
Sr.No | Area | Project | Description | P Start Date | P End Date | A Start Date | Revised Closer date | Current Date | Days | A End Date | Owner | Status | Remark as on 11-Aug-21 | Remark as on 18-Aug-21 | Remark as on 25-Aug-21 | Remark as on 01-Sep-21 | Remark as on 08-Sep-21 | Remark as on 15-Sep-21 | Remark as on 22-Sep-21 | Remark as on 29-Sep-21 | Remark as on 06-Oct-21 | Remark as on 13-Oct-21 | Remark as on 19-Oct-21 | Remark as on 27-Oct-21 | Remark as on 18-Nov-21 | Remark as on 05-Dec-21 | Remark as on 29-Dec-21 | Remark as on 12-Jan-22 | Remark as on 28-Jan-22 | Remark as on 02-Feb-22 | Remark as on 09-Feb-22 | Remark as on 17-Feb-22
1 | AMS | Development of Admin Inventory Module. | Admin Inventory module to generate online PO and maintain approval matrix. | 2019-10-05 | 2020-08-21 | 2019-10-05 |  |  |  | 2020-08-21 | Ajinkya | Completed
2 | IMS | ITIL Helpdesk Implementation | Sapphire Implementation | 2020-03-01 | 2020-05-15 | 2020-03-01 |  |  |  | 2020-05-01 | AHFL IT | Completed
3 | AMS | Document Migration in TCS DMS. | Migration of all customers scanned document from Aadhar storage to TCS DMS. | 2020-03-06 | 2020-07-16 | 2020-03-06 |  |  |  | 2020-07-16 | Ajinkya | Completed
4 | AMS | Implementation Tresuary Module | Implementation of credence Treasury module in New data centre. | 2020-03-20 | 2020-08-01 | 2020-03-20 |  |  |  | 2020-08-01 | Ajinkya | Completed
5 | IMS | DC DR Migration | DC DR Track | 2020-03-15 | 2020-08-31 | 2020-03-25 |  |  |  | 2020-09-27 | TCS/AHLF IT | Completed
6 | AMS | Implementation and Setup of Synergy and No- Platform Applications in TCS Data Center. | New I series and other windows server setup in New Data center.Includes Synergy core Application and Application like 3i portal, FI portal, Online Pay, Cognos etc.. | 2020-03-25 | 2020-07-13 | 2020-03-25 |  |  |  | 2020-07-13 | Ajinkya | Completed
7 | AMS | CLSS Old data Submisssion to NHB through API. | API integration to submit Old CLSS data to NHB. | 2020-03-28 | 2020-09-15 | 2020-03-28 |  |  |  | 2020-09-15 | Ajinkya | Completed
8 | AMS | Development of Moratorium Feature in Core Synergy Module. | As per government guidelines on Covid New Moratorium feature develop in Synergy Application. | 2020-03-31 | 2020-04-06 | 2020-03-31 |  |  |  | 2020-04-06 | Ajinkya | Completed
9 | AMS | Paytm Android Application for Collection | Deploy Aadhar payment API in Paytm Mobile Application. | 2020-04-29 | 2020-09-02 | 2020-04-29 |  |  |  | 2020-09-02 | Ajinkya | Completed
10 | IMS | CPU migration I | Bhandup to Andheri | 2020-03-25 | 2020-03-30 | 2020-05-05 |  |  |  | 2020-05-10 | Sachin /Helpdesk team | Completed
11 | AMS | CRM API Integration. | API integration to submit real time customer details from Synergy system to CRM. | 2020-05-11 | 2020-10-21 | 2020-05-11 |  |  |  | 2020-10-21 | Ajinkya | Completed
12 | AMS | Paytm Wallet Imeplementation. | Implementation of Paytm wallet so Customers can able to pay o/s from website. | 2020-06-11 | 2020-10-15 | 2020-06-11 |  |  |  | 2020-10-15 | Ajinkya | Completed
13 | IMS | Endpoint Antivirus implementation | Falcon AV implementation | 2020-06-01 | 2020-07-31 | 2020-06-15 |  |  |  | 2020-08-31 | Sachin /Helpdesk team | Completed
14 | AMS | Iseries Data BackUp Setup in TCS DC. | Established and setup Backup Scheduled backup facility of DB2 synergy database in DC. | 2020-06-24 | 2020-06-26 | 2020-06-24 |  |  |  | 2020-06-26 | Ajinkya | Completed
15 | IMS | Endpoint Domain Migration | Manual Endpoint Domain | 2020-07-05 | 2020-08-10 | 2020-07-05 |  |  |  | 2020-08-30 | Sachin /Helpdesk team | Completed
16 | AMS | ACE scoring calculation of OLD Aadhar Customers. | Generate ACE score for all OLD customers. | 2020-08-10 | 2020-10-22 | 2020-08-10 |  |  |  | 2020-10-10 | Ajinkya | Completed
17 | IMS | DR setup | iseres , 3i and Treasury applications at DR | 2020-08-15 | 2020-09-15 | 2020-12-15 |  |  |  | 2021-01-27 | Rajesh K L | Completed
18 | AMS | Implementation and Setup of Synergy and No- Platform Applications in TCS DR. | New I series and other windows server setup in DR.Includes Synergy core Application and Application like 3i portal, Tresuary,Cognos etc.. | 2020-09-10 | 2020-10-04 | 2020-09-10 |  |  |  | 2020-10-04 | Ajinkya | Completed
19 | IMS | IT Asset Management Implementation | IT Governance improvement | 2020-09-15 | on going project | 2020-09-15 |  | 2022-04-18 | 580 |  | Prajakta/Ashish | WIP | Admin Live:-2214 Match with Sapphire :- 1900 Missing System :- 316 (9 worng serial number in admin sheet share with manthan and 6 system remove from sapphire because system replace with new system) Final count is 301 | Admin Live:-2214 Match with Sapphire :- 1916 Missing System :- 300 (9 worng serial number in admin sheet share with manthan and 6 system remove from sapphire because system replace with new system) Final count is 285 | Admin Live:-2214 Match with Sapphire :- 1916 Missing System :- 300 (9 worng serial number in admin sheet share with manthan and 6 system remove from sapphire because system replace with new system) Final count is 285 | Admin Live:-2214 Match with Sapphire :- 1948 Missing System :- 265 (17 worng serial number in admin sheet share with manthan / 9 system remove from sapphire because system replace with new system/6 system replace) Final count is 233 | Admin Live:-2214 Match with Sapphire :- 1961 Missing System :- 252 (16 worng serial number in admin sheet share with manthan / 10 system remove from sapphire because system replace with new system/6 system replace) Final count is 220 |  | AS PER NEW Admin Live:-2559 Match with Sapphire :- 2152 Missing system count _-4077 Removed :- 83 System not working :-36 Not Configured:- 33 Sapphire installation pending:-24 System not available:-16 Not Found in sapphire post installation sapphire client:-09 Replace:-05 Installation issue :-1 Branch close:-1 (Ambala ) | WIP | AS PER NEW Admin Live:-2559 Match with Sapphire :- 2164 Missing system count _-395 Removed :-106 System not working :-31 Not Configured :-19 Sapphire installation pending :-23 System not available :-10 Replace :-5 Installation issue :-1 | AS PER NEW Admin Live:-2559 Match with Sapphire :- 2182 Missing system count _-377 Remark pending :-145 | AS PER NEW Admin Live:-2559 Match with Sapphire :- 2184 Missing system count _-375 Remark pending :-145 (Same no remark add) | AS PER NEW Admin Live:-2559 Match with Sapphire :- 2184 Missing system count _-375 Remark pending :-145 (Same no remark add) |  |  |  |  | ON Goining ptojrect | As checked with Admin sheet 282 systems are not reflecting in sapphire Total Asset by Admin- 2659 Total assets by sapphire- 2707 | Admin Inventory 3156 Sapphire Inventory 2708 Desktop/Laptop Inventory as per Admin:- 2659 Desktop/Laptop Inventory as per Sapphire:-2678 Not in Sapphire but available in Inventory:-282 Not in Admin Inventory but available in Sapphire 301
20 | IMS | CPU Migration II | Andheri to Thane | 2020-09-01 | 2020-09-05 | 2020-09-19 |  |  |  | 2020-09-25 | Sachin /Helpdesk team | Completed
21 | AMS | Lotus Domino Deployment on Windows Server. | After lots of efforts successfully able to deploy and run Lotus Domino application on windows server. This help to transfer Users load from I series server. | 2020-10-04 | 2020-10-08 | 2020-10-04 |  |  |  | 2020-10-08 | Ajinkya | Completed
22 | IMS | Mobile email security implementation | Mobile device management | 2020-10-05 | 2020-12-15 | 2020-09-23 |  |  |  | 2020-12-20 | Gyan, Sachin | Completed
23 | AMS | Development of Ex-gratia functionality in Synergy Module. | As per government guidelines Ex-Gratia feature develop in Synergy Application. | 2020-10-31 | 2020-11-05 | 2020-10-31 |  |  |  | 2020-11-05 | Ajinkya | Completed
24 | IMS | Network BANDWITH Review Upgrade | MPLS branch link upgrade project | 2020-11-18 | 2021-01-18 | 2020-11-20 |  |  |  | 2021-06-05 | Rajesh /Praful | Completed
25 | IMS | DR Drill | DR drill to ensure the BCP and Statutory requirement | 2020-12-12 | 2020-12-12 | 2020-12-12 |  |  |  | 2020-12-12 | IT Team | Completed
26 | IMS | Software compliance and upgrade for Endpoints | OS upgradtion | 2020-02-01 | 2021-03-31 | 2020-12-15 |  |  |  | 2021-03-31 | Sachin /Helpdesk team | Completed
27 | IMS | Policy Review | policy documents and procedures (36) Item reviewed and present to board | 2020-12-15 | 2021-06-30 | 2020-12-15 |  |  |  | 2021-05-11 | Rajesh | Completed
28 | IMS | Hardware Upgrade (Desktop/Laptop) | Performance stability and OS compliance | 2020-12-25 | 2021-04-30 | 2020-12-23 |  |  |  | 2021-04-30 | Rajesh/ Divya | Completed
29 | IMS | Archival Storage at low cost ( Hitachi storage G130) | Evaluation and implementation of low cost storage | 2021-01-05 | 2021-03-31 | 2021-01-27 |  |  |  | 2021-09-18 | Praful/Gyan/Vishwanath | Completed |  | WIP | WIP |  | Need to close | Want Close date
30 | IMS | AD GROUP ID MODIFICATION | modification of all (550) group ID'S | 2021-01-17 | 2021-01-24 | 2021-01-17 |  |  |  | 2021-01-24 | Gyan | Completed
31 | IMS | NAS Migration Data | Transfer Onprin data to words TCS Cloud | 2020-12-05 | 2021-02-28 | 2020-12-05 |  |  |  | 2021-08-29 | praful/Vishwanath | Completed | Data was copied but the Rights were not transferred succesfully so a rollback was take n on 9th Aug midnight to the old data. |  | Account folder completed/Resigned employee old backup folder pending | Project completed
32 | IMS | WIFI controller setup | Security for wifi access point | 2020-11-20 | 2021-01-05 | 2021-01-06 |  |  |  | 2021-02-20 | praful | Completed
33 | IMS | AD Audit Pluse POC | For Auditing Purpose | 2021-02-04 | 2021-02-08 | 2021-02-04 |  |  |  | 2021-02-10 | GYAN | Completed
34 | IMS | SD WAN | SD WAN DATA CENTER implementation (target 49 branches) | 2021-02-24 | 2021-03-10 | 2021-02-24 |  |  |  | 2021-09-22 | praful | Completed | Some sites were reported slow accessibility after implementation, so a Troubleshooting Session is initiated with nexapp team for the same, rest sites were on hold due to the slowness issue. | Status Total Live 26 Initiated with Nexapp 7 Grand Total 33 | Status Total Live 28 Initiated with Nexapp 5 Grand Total 33 | Status Total Live 28 Initiated with Nexapp 5 Grand Total 33 Estimated Completion By Nexapp shared as on 3-09-2021 | Status Total Live 29 Initiated with Nexapp 4 Grand Total 33 | Status Total Live 29 Initiated with Nexapp 4 Grand Total 33 | Status Total Completed 30 Out OF SCOPE 1 NO ISP AVAILAblE 2 Grand Total 33
35 | AMS | Dialler Integration Torous API Publish to send the cases from DOB | TCS platform Dialler integration for leads | 2021-01-21 | 2021-04-17 | 2021-01-21 |  |  |  | 2021-04-17 |  | Completed
36 | AMS | HR Enrolment Project | Automation of on boarding and approval workflow for off-role employees with vendors such as teamlease. | 2021-01-01 | 2021-04-08 | 2021-01-01 |  |  |  | 2021-04-08 | Nikhil B/Dilip. | Completed
37 | AMS | Airtel BBPS (ONLINE PAYMENT) | Integration with Bharat Bill pay through Airtel bank | 2021-01-12 | 2021-03-30 | 2021-01-12 |  |  |  | 2021-03-30 | Nikhil B | Completed
38 | AMS | Airtel Customer Model | Integration with Airtel bank for Lead referral | 2021-01-12 | 2021-03-30 | 2021-01-12 |  |  |  | 2021-03-30 | Nikhil B | Completed
39 | AMS | TCS Payment API Import to AHFL WSO2 | Current live Payment API (Payment aggregators , Razorpay, paytm,paynearby etc)to be integrated with TCS payment systems. | 2021-01-01 | 2021-03-30 | 2021-01-01 |  |  |  | 2021-03-30 |  | Completed
40 | AMS | DOB Website Testing | Lead submission page on Aadhar web site to be developed and integrated with TCS platform. | 2021-01-01 | 2021-03-30 | 2021-01-01 |  |  |  | 2021-03-30 |  | Completed
41 | AMS | Separate MySQL DB for every Project on Process Maker Ubuntu | Audit Compliance requirement for Database management. | 2021-02-15 | 2021-04-30 | 2021-02-15 |  |  |  | 2021-04-15 |  | Completed
42 | AMS | AD Integration with Ubuntu Process Maker | PIM For DC and DR | 2021-02-19 | 2021-02-19 | 2021-02-19 |  |  |  | 2021-02-19 |  | Completed
43 | AMS | CRM Cases re-submission |  | 2021-04-01 | 2021-04-28 | 2021-04-01 |  |  |  | 2021-04-28 | Nikhil B/Chandan | Completed
44 | AMS | TCS internal and external Integration. |  | 2021-04-04 |  | 2021-04-04 |  | 2022-04-18 | 379 |  | Nikhil B /Sharad Sir/Ajinkya | WIP | WIP | [5 empty] | Need to Publish MIS
45 | AMS | e-mandate Cancellation |  | 2021-04-05 | 2021-05-05 | 2021-04-05 |  |  |  | 2021-05-05 | Nikhil B/Nirav/Mahesh. | Completed
46 | AMS | E-Mandate New registration |  | 2021-04-05 | 2021-05-30 | 2021-04-05 |  |  |  | 2021-05-13 | Nikhil B/Nirav/Mahesh. | Completed
47 | AMS | Credence Treasury application Setup. |  | 2021-04-05 |  | 2021-04-05 |  |  |  | 2021-09-13 | Nikhil Kadam/Ajinkya | Completed | UAT in progress with treasure user. |  |  |  | 13-sep-2021 on live |  | Awaiting for Production
48 | AMS | TCS Data Migration |  | 2021-04-05 | 2021-08-15 | 2021-04-05 |  | 2022-04-18 | 378 | 2022-02-01 | Animesh/Nikhil | Completed | Cycle 7 done will be sending to TCS. |  |  |  | 2 Templets pending | [13 empty] | Final Test Sign- Off received from AQM on 01 Feb 2022
49 | IMS | ProDmarc, Prodiscover and Prophish Licenses | Dmarc and prophising Implementation | 2021-04-09 | 2021-09-30 | 2021-04-09 |  |  |  | 2021-06-28 | Gyan | Completed
50 | IMS | ANB Audit Actionable | 21 Audit Observation Open Point | 2021-04-23 | 2021-06-30 | 2021-04-23 |  |  |  | 2021-09-11 | AMS/IMS Team | Completed | 44 (Observation point) 04 open Point 40 close Point | 44 (Observation point) 04 open Point 40 close Point | 44 (Observation point) 04 open Point 40 close Point | 44 (Observation point) 04 open Point 40 close Point | 44 (Observation point) 04 open Point 40 close Point | 44 (Observation point) 01 open Point 43 close Point
51 | IMS | Link Migration -TCS to AHFL-Squid Proxy/FP Proxy | Whitelist the new Proxy public IP 115.112.115.236 at the vendor end Airtel / CIBIL and Razor Pay ( Same public IP 115.112.115.236 can be used for outbound traffic) | 2021-04-23 | 2021-07-10 | 2021-04-23 |  |  |  | 2021-07-22 | NikhilB/Viswanath/Praful/TCS | Completed
52 | AMS | HR Off role Production integration with Work line Label:-1 (HR Off roll master data integration -1) Label :2 (HR Off roll process create employee integration -02) |  | 2021-04-26 | 2021-06-30 | 2021-04-26 |  |  |  | 2021-08-02 | Nikhil B. | Completed
53 | AMS | Lead creation from Synergy for infligh cases.(POC) |  | 2021-04-26 | 2021-05-30 | 2021-04-26 |  |  |  | 2021-05-30 | Nikhil B. | Completed
54 | IMS | 2FA Implementation on O365 Web mail |  | 2021-05-18 | 2021-06-01 | 2021-05-18 |  |  |  | 2021-06-11 | Gyan/ Ashish | Completed
55 | IMS | AD Manager Plus /AD Audit Plus |  | 2021-05-21 | 2021-06-30 | 2021-05-21 |  |  |  | 2021-06-28 | GYAN | Completed
56 | IMS | HYBRID AGENT INSTALLATION |  | 2021-05-25 | 2021-08-15 | 2021-05-25 |  |  |  | 2021-08-31 | Sachin /Helpdesk team | Completed | 554 agent installation done | 561 agent installation done | 561 agent installation done | 570 agent installation done
57 | AMS | Resigned employee integration with synergy |  | 2021-06-01 |  | 2021-06-01 |  | 2022-04-18 | 321 | 2021-09-08 | Nikhil B/Saravana | Drop Project | API scheduler error detected, working on it by Nikhil B/ Final testing is pending with API by Saravana |  |  |  | Drop project
58 | AMS | SCD deployment on server |  | 2021-06-06 |  | 2021-06-06 |  | 2022-04-18 | 316 |  | Srikanth/Nikhil B | On Hold | Kept onhold |  |  |  | ON HOLD
59 | IMS | VAPT |  | 2021-06-08 | 2021-07-10 | 2021-06-08 | 2021-08-31 | 2022-04-18 | 314 |  | Vishwanathan | On Hold | Production patching completed:-1290 Pending:-110 %:--92 % done 8 Host IP Pending | Production patching completed:-1290 Pending:-110 %:--92 % done 8 Host IP Pending | Production patching completed:-1290 Pending:-110 %:--92 % done 8 Host IP Pending | Production patching completed:-1290 Pending:-110 %:--92 % done 8 Host IP Pending | Production patching completed:-1293 Pending:-107 %:--92 % done 8 Host IP Pending | Production patching completed:-1293 Pending:-107 %:--92 % done 8 Host IP Pending | ON HOLD | ON HOLD
60 | AMS | Online Portal MySQL Data auto triggered functionality for business users |  | 2021-06-16 |  | 2021-06-16 |  |  |  | 2021-09-10 | Nikhil K | Completed | WIP |  | Deployment pending | Deployment pending | Deployment date 09-09-2021
61 | AMS | Treasury document DMS upload setup & Migration. |  | 2021-06-16 |  | 2021-06-16 |  | 2022-04-18 | 306 |  | Nikhil Kadam/Ajinkya | WIP | Awaiting for reponse from TCS on development |  |  |  | UAT Complted awaiting for sing-off
62 | AMS | IPPB Mobile App POC |  | 2021-07-06 |  | 2021-07-06 |  |  |  | 2021-09-21 | Ajinkya/Nikhil B. | Completed | Server allocation completed, Application implemetation in process |  |  |  | Sign-off Received / VAPT is in progress
63 | AMS | InFlight Cases DMS upload data with API from 3i BPO to TCS |  | 2021-07-10 | 2021-08-05 | 2021-07-10 |  |  |  | 2021-08-05 | Nikhil B | Completed | Testing completed, issues wip with tcs team
64 | IMS | SCD for Windows 2012 and window 2016 |  | 2021-08-08 | 2022-03-15 | 2021-08-08 |  | 2022-04-18 | 253 |  | Shalmali/Vishwanath | WIP |  |  | CR raised no update from TCS Team | WIP |  | On Hold | Follow-email has been sent. Awaiting for reverts from TCS | TCS will share plan of action as per SCD points 246, in current scenario TCS reviewing 246 points | Under Review by TCS Team | SCD Review almost completed by TCS, Today Deviprasad will share Review Document | Waiting for TCS Reply | WIP | 3I DB(MS SQL): DR server(10.220.0.8) Test username created for testing SCD points on above DR server. | Pending from TCS (User name or Pwd not authenticate on DR Server10.220.0.8 |  | Pending for TCS end /as Discussed with Antony we do join call with Devi Prasad | awaiting for revert from TCS | UAT 3i or FI server need to be selected from tesing DC for the same user creation in progess | UAT 3iBPO server is selected for testing .scdtestuser created and policy is being deployed. Awaiting for update from TCS.
65 | IMS | Bit locker windows 10 Testing |  | 2021-08-19 | 2022-03-15 | 2021-08-19 |  |  |  | 2021-09-22 | Sachin | Completed |  |  |  |  | Need Document preparation | Rajesh Sir mail send the TCS (Waiting for mail reply | - | POC indivial system is completed
66 | IMS | Cyber Insurance – Proposal |  | 2021-08-23 | 2021-11-30 | 2021-08-23 |  |  |  | 2021-12-29 | Rajesh KL /Sharad | Completed | [5 empty] | - | - | Initial data is shared awaiting the praposal new project need to be created for centerlized key management | Additional data to be submitted |  |  |  | As on 18-Nov-21 Proposal recevied final approval to be raised | -
67 | AMS | ADF integration project |  | 2021-08-30 | 2021-09-30 | 2021-08-30 |  | 2022-04-18 | 231 |  | Ajinkay Sir/Animesh | WIP |  |  |  | WIP | Infra Inciation is pending | [11 empty] | Server Completed |  | Data Quality issue is observed for 20k+ cases and Project is awaiting clean data from Business
68 | IMS | Senior Management Hybrid agent installation |  | 2021-08-31 |  | 2021-08-31 |  | 2022-04-18 | 230 |  | Sachin | On Hold |  |  |  |  | 576 | Higher Management Communication Mailer send to Rajesh Sir | On Hold
69 | IMS | SCD for Windows -10 Hardening Document |  | 2021-09-08 | 2022-03-15 | 2021-09-08 |  | 2022-04-18 | 222 |  | Denial/Sachin | WIP | [5 empty] | One policy under Observation | One Policy Observation pending | 1 observation pending today sachin will complete the same | changes to be done |  | We have shared observation on SCD- those points is pending to be reviewed by TCS. | We have shared observation on SCD- those points is pending to be reviewed by TCS. |  |  | We are timely share implemented hardening policy obsevation with TCS, still pending from TCS site | we have asked Rupesh to intervene | windows-10 2 points pending | Observation has been shared,Pending from the TCS | Pending from the TCS
70 | IMS | IT Risk Register Update for current Year |  | 2021-09-16 | 2022-03-15 | 2021-09-16 |  | 2022-04-18 | 214 |  | GYAN | WIP | [6 empty] | WIP | Identified Critical servers | 40% Completed | 60% Completed | 60% Completed | 60% Completed |  | Confirmation pending from rajesh sir side | Confirmation pending from rajesh sir side | Confirmation pending from Rajesh sir side | Confirmation pending from Rupesh Vedante | Confirmation pending from Rupesh Vedante | Confirmation pending from Rupesh Vedante
71 | IMS | Hitachi Archival | • Verifying current data status in TCS. • After getting data confirmation sending Hitachi storage to TCS • Copying complete data in Hitachi storage in know file system format ( Windows NTFS) • Bring backup Hitachi archival to Thane office location. | 2021-09-22 | 2021-10-30 | 2021-09-22 |  |  |  | 2021-01-06 | Vishwanath | Completed | [7 empty] | Data transfer is initiate |  | Storage box sending to TCS Data center | Storage box sending to TCS Data center | Storage box sending to TCS Data center |  | Hitachi storage bringing back to Thane office in this week | Hitachi sersver at thane office | Completed
72 | AMS | IPPB Collection integration |  | 2021-09-08 |  | 2021-09-08 |  | 2022-04-18 | 222 |  |  | WIP | [6 empty] | Technical Discussion ids completed , Documentation part is pending with business
73 | AMS | Volt MX server setup and software installation |  | 2021-08-23 | 2021-09-13 | 2021-08-23 |  | 2022-04-18 | 238 |  | Suraj | WIP |  |  |  |  | waiting for Root user rights |  |  | Installation is completed, But getting error when activating license, and issue raised with HCL team and daily follow up with team.
74 | IMS | windows 7 systems are upgraded to Windows 10. | Need to remove window 7 system from sapphire if system replace with window 10 | 2021-06-07 | 2022-02-25 | 2021-06-07 |  | 2022-04-18 | 315 | 2022-02-03 | Divya | Completed | [7 empty] | Window 7 total count:=342 Remove Count:-237 Cureent system show in Sapphire:-105 (74 system still in use / remaining 31 system waiting for branch reply | Cureent system count is 109 need to check | 109 System show in sapphire waiting for remark 34 system (29 Branches) 75 System still in use respective branches (data already share with admin team) | 108 System show in sapphire waiting for remark 33 system (29 Branches) (List share with Dinesh M) 75 System still in use respective branches (data already share with admin team) | 103 System show in sapphire waiting for remark 29 system (24 Branches) (List share with Dinesh M) 1 system not found 73 System still in use respective branches (data already share with admin team) |  |  | Total :-108 Still in use :-72 (18 system are not loged in since 30 days) Remove systems again show in inventory(3) System not foun:-1 already window 10:-1 Remark Pending:31 | Total :-108 Still in use :-72 (18 system are not logged in in the last 30 days) Remove systems again show in inventory(3) System not found:-1 already window 10:-1 Remark Pending:31 | All 108 inactive window 7 systems list share with Aashish and Rajesh Sir (want End date to close date | All 108 inactive window 7 systems list share with Aashish and Rajesh Sir (want End date to close date | Sheet share with Prajakta (Need to closed)
75 | IMS | Geo-fencing project |  | 2021-09-09 | 2021-09-30 | 2021-09-09 |  |  |  | 2021-09-24 | Shalmali | Completed
76 | IMS | Zoho Desk and Zoho assist Evaluation | Support platform evaluation for External customers | 2021-09-01 | 2021-09-30 | 2021-09-01 |  |  |  | 2021-09-30 | Sachin | Completed
77 | IMS | Google Chrome browser update | TCS website prerequisites | 2021-10-11 | 2021-11-10 | 2021-10-11 |  |  |  | 2021-11-10 | Sachin | Completed | [10 empty] | 656 systems are completed with latest version of chrome. | 656 systems are completed with latest version of chrome. | 820 systems are completed with latest version of chrome.
78 | AMS | DB2 FD database setup plan |  | 2021-11-01 |  | 2021-11-01 |  | 2022-04-18 | 168 |  | Suraj | WIP
79 | IMS | DLP Implemetion In office 365 |  | 2021-11-12 | 2021-11-18 | 2021-11-12 |  |  |  | 2021-11-18 | Gyan | Completed
80 | IMS | Web Mail Restriction |  | 2021-11-19 | 2021-12-04 | 2021-11-19 |  |  |  | 2021-12-04 | Gyan | Completed | [12 empty] | Production deployment pending | Implemented
81 | IMS | DLP ISE Migration |  | 2021-10-01 | 2022-01-30 | 2021-10-01 |  | 2022-04-18 | 199 | 2022-01-24 | Gyan | Completed | [12 empty] | Port opening request pending | Port opening request pending |  | Migration will be completed Next week | Migration will be completed Next week | Migration has been done
82 | IMS | GTB DLP Implemetion |  | 2021-11-26 | 2022-02-15 | 2021-11-26 |  | 2022-04-18 | 143 |  | Gyan | WIP | [12 empty] | Sever provisning pending | Port opening pending last 7 days |  | POC On going | POC On going | Policies have been created, we have tested police's, 1. USB policy done 2. Cloud policy done 3. Gmail policy done 4. Keywords policy done 5. Web policy done 6. Whitelist urls done 7. Clasification Pending Task Mobile policy is confirmed. Data Spacific policy Discovery | Pending Task Mobile policy is confirmed. Data Spacific policy Discovery
83 | IMS | Q3 server patching |  | 2021-10-08 | 2022-02-15 | 2021-10-08 |  | 2022-04-18 | 192 |  | Sachin/Vishwanath | WIP | [13 empty] | manegamnet 7 server pending |  | UAT Server completed /management Completed /Production server pending | UAT Server completed /management Completed /Production server pending | UAT Server completed /management Completed /DR server patching in progress | Production Sever Pending we will take that server with VA
84 | IMS | DR Decommission Project November-December 2021 |  | 2021-11-27 | 2021-12-30 | 2021-11-27 |  |  |  | 2021-12-28 | Ajinkya/rajesh/Animesh/Sharad Sir | Completed
85 | IMS | Bandwidth Upgrade Project | Bandwidth Upgrade Project tracker for 52 Locations | 2021-11-01 | 2021-12-28 | 2021-11-01 |  | 2022-04-18 | 168 |  | Praful | WIP | [13 empty] | Tata Link Upgraded:-5 Upgradation with parallel new link :-6 Pending with rajendra:-1 Pending :-24 Total:- 36 Sify:-Pending 18 | Tata (36) Link Upgraded:-11 Pending with PM:-11 COF Signed Order Logged:-10 Upgradation with Parallel new link:-4 Sify: 18 Link Upgraded:-12 Order with PM for Upgrade:-6 | Tata (36) Link Upgraded:-11 Pending With Rajendra:-21 Upgradation with Parallel new link:-4 Sify: 18 Link Upgraded:-17 Upgrade not required:-1 | Tata (36) Link Upgraded:-13 Pending With Rajendra:-20 Upgradation with Parallel new link:-3 Sify: 18 Link Upgraded:-17 Pending With IM:-1 | NO any progress from last week, Praful has send the revised commerical. | Need updated status
86 | IMS | Samsung Tablet POC |  | 2021-12-06 | 2022-01-20 | 2021-12-06 |  |  |  | 2021-12-30 | Ashish | Completed | [16 empty] | Implementaion Pending
87 | IMS | Data Erase from Scrap systems- PAN India |  | 2022-01-05 | on going project | 2022-01-05 |  | 2022-04-18 | 103 |  | Denial/Sachin | WIP | [15 empty] | data erase for e-waste management | data erase for e-waste management | in process | in process
88 | IMS | Hybrid proxy installation in other than MPLS branches |  | 2022-01-05 | 2022-02-20 | 2022-01-05 |  | 2022-04-18 | 103 |  | Denial/Sachin | WIP | [15 empty] | Hybrid proxy at micro branches | Hybrid proxy at micro branches | hybrid proxy installed in 70 system | hybrid proxy installed in 80 system (Project kept in hold Pending for deployment tool PDQ)
89 | IMS | AD Self Services |  | 2022-01-10 | 2022-02-02 | 2022-01-10 |  | 2022-04-18 | 98 |  | Gyan | WIP | [15 empty] | Pre Request is initiated | pre-requisites | IP whitelist pending from Equance team | Creating new API URL
90 | AMS | HR Offrole hiring portal integration with workline |  | 2021-10-01 |  | 2021-10-01 |  |  |  | 2021-11-30 | Nikhil B/Gyan | Completed
91 | AMS | Ghar Vapsi Portal for HR |  | 2022-01-01 |  | 2022-01-01 |  |  |  | 2022-01-20 | Shantanu/Sourab | Completed
92 | AMS | Axis SFTP Automation Process |  | 2021-11-01 |  | 2021-11-01 |  |  |  |  | Nikhil K/ Nikhil B | Completed
93 | AMS | AHFL Website PayTM Automated Posting |  | 2021-11-01 |  | 2021-11-01 |  | 2022-04-18 | 168 |  | Shantanu/Nikhil B | WIP
94 | AMS | Webpage Lead Integration |  | 2021-11-01 |  | 2021-11-01 |  |  |  |  | Shantanu/Nikhil B | Completed
95 | AMS | Pro CS Application for Board Meeting |  | 2021-11-01 |  | 2021-11-01 |  |  |  | 2021-11-20 | Srikanth | Completed
96 | CTB | Customer welcome Kit automation |  | 2021-11-01 |  | 2021-11-01 |  | 2022-04-18 | 168 |  | kuareshan/Ajinkay | WIP
97 | CTB | Customer Service App |  | 2022-01-01 |  | 2022-01-01 |  | 2022-04-18 | 107 |  | kuareshan/Ajinkay | WIP
98 | CTB | Sales Mobility App | [5 empty] | 2022-04-18 |  |  | kuareshan/Ajinkay | WIP
99 | CTB | Video PD solution & Credit Query Resolution through WhatsApp | [5 empty] | 2022-04-18 |  |  | kuareshan/Ajinkay | WIP
100 | CTB | Digital Stamping |  | 2021-08-01 |  | 2021-08-01 |  | 2022-04-18 | 260 |  | kuareshan/Ajinkay | On Hold
101 | CTB | Online Audit Management module |  | 2022-01-25 |  | 2022-01-25 |  | 2022-04-18 | 83 |  | kuareshan/Ajinkay | WIP
102 | IMS | AD Integration with Work line |  | 2021-11-01 |  | 2021-11-01 |  | 2022-04-18 | 168 |  | Gyan/ Nikhil B | On Hold | [16 empty] | ON Hold
103 | AMS | Umang App Integration |  | 2021-12-15 |  | 2021-12-15 |  | 2022-04-18 | 124 |  | Nikhil B/Shantanu | WIP
104 | AMS | RPA POC |  | 2021-12-01 |  | 2021-12-01 |  | 2022-04-18 | 138 | 2021-01-15 |  | Completed
89 | IMS | IT Asset Disposal |  | 2022-02-08 |  | 2022-02-08 |  | 2022-04-18 | 69 |  | Prajakta | WIP | [18 empty] | Mark mail to Admin for providing consolidate list of to be dispose assets to decide further course of action.
89 | IMS | IMAC Process |  | 2022-02-08 | On Goining | 2022-02-08 |  | 2022-04-18 | 69 |  | Prajakta | WIP | [18 empty] | Follow up with Sapphire team to configure and fine tuned IMAC process configured in Tool. Revert from Sapphire support team are yet to receive.
Completed
WIP
Not Started
Drop Project
On Hold